## Grant Transfer to UD
Transfer to UD Responsibility Matrix/Checklist
Transfer to UD | PI | DA | C/G | SRA | Sponsor
INITIAL ACTIONS
Arrange initial meeting to identify the portfolio of award(s), coordinate checklist activities and path forward | X | X | X
Verify academic start date; Provide copy of the offer letter to UD Contract and Grants Specialist (CGS) | X | X
Provide Award relinquishing letter/form from your previous instituion (if applicable) | X | X
Provide CGS with contact information of the Sponsored Research Office at previous institution | X | X
Establish bi-weekly meeting with PI and Department Administrator to review status of transfer |  |  | X
TRANSFER PROCESS
Work with the sponsored research contact at the PI’s previous institution and the sponsor to coordinate activities for transfer |  |  | X
Contact sponsor and request/obtain any required documents |  |  | X
Provide a copy of the original award notice and a detailed budget of the remaining funds using UD’s fringe benefit and F&A rates to your CGS | X | X
Provide details of any cost share agreements in effect for the new proposal and budget to CGS | X | X
Submit any animal or human subject protocols (submitted to the Compliance Manager) | X
Compile agency specific requirements/forms |  |  | X
Provide subrecipient SOW, detailed budget, Provider Determination worksheet, and contact information to CGS, as applicable | X | X
FINAL ACTIONS
Review award from previous institution and compare to anticipated award amount |  |  | X
Proceed with process for proposal webform approval | X | X | X
Submit package to sponsor |  |  | X
Address follow-up questions from sponsor |  |  | X
Issue Award Notice to UD |  |  |  |  | X
Proceed with process for award set up |  |  | X
Initiate FIN Requisition/Vendor Payment Request for subawards (if applicable) |  | X
Issue subaward documents (if applicable) |  |  | X
Initiate consultant agreements (if applicable) |  |  | X
Provide Department Administrator and General Accounting (Karen Brown) with details to arrange for the transfer of equipment, as applicable | X | X
Note on A4: pgarvey: Fellowships may require that fellow remain fellow at originating institution - this require clear communication with fellowship office of originating institution.